# APIX LLMOps Platform

Project Implementation Plan

Prepared: 2026-10-08   |   Delivery approach, WBS, estimates, timeline, team, and RAID.

# 1. Delivery Approach

Phase-based, dependency-sequenced (not feature-cut). Phase 1 Foundation (platform core + Ops Platform + APIX end-to-end + launch) -> Phase 2 Scale & Optimize (throughput, FinOps, caching) -> Phase 3 Operational Maturity (release promotion, kill-switch, deprecation) -> Phase 4 Reuse & Expand (second use case by config).

# 2. Scope Summary

In: LLMOps core, Ops Platform (11 modules), APIX app (ingestion to reporting), user onboarding. Out: second use case build; real-time/streaming ingestion.

# 3. RAID Log

## 3.1 Decisions / Open Items

| ID | Decision | Impacts |
| --- | --- | --- |
| D-1 | Compliance/regulatory standards | Guardrails, retention, security, Content Safety cost |
| D-2 | Expected scale (calls/day, users) | Infra sizing, cost, throughput |
| D-3 | Final program list + KPI rulebooks | KPI engine, golden data scope |
| D-4 | Governance ownership + advisory vs approval | Feedback flow, governance module |
| D-5 | Registry store: Cosmos vs Azure SQL | Data architecture, persistence |
| D-6 | Delivery team model | Timeline, capacity |
| O-1 | Data dictionary detail | SRS completeness |
| O-2 | Retention values | Security/data design |
| O-3 | BR-FR-test matrix | Test design |
| O-4 | Network topology / landing zone | Deployment design |

## 3.2 Risks

| ID | Risk | Mitigation |
| --- | --- | --- |
| R-1 | Content Safety on 100% of calls could cost $2.3-6k/mo | Layered guardrails; Content Safety selective |
| R-2 | KPI composite score unfair across programs | Redefine per-program; validate vs SME samples |
| R-3 | Golden-data certification bottleneck | Prioritize probes; 2-reviewer queue; grow over time |
| R-4 | Azure OpenAI rate limits at full volume | Batching, retry/backoff, provisioned throughput (P2) |
| R-5 | Decisions delayed -> work slips | Track D-1..D-6 from week 1; parallelize |

## 3.3 Assumptions

POC prompts reusable as v1; Azure access provisioned; SMEs available; POC architecturally sound (rebuild, not re-invent).

# 4. Work Breakdown Structure

| Epic | Key stories | Est. (days) |
| --- | --- | --- |
| E1 Discovery & decisions | Confirm D-1..D-6; translate compliance/scale/programs | 15 |
| E2 Platform foundation | Repo, envs, CI/CD, config-as-code, Key Vault/identity | 20 |
| E3 Prompt management | Registry, versioning, activate/rollback, diff, stamping | 18 |
| E4 Model management | Alias->deployment, task binding, pinning | 15 |
| E5 Evaluation gate | Golden framework, probe eval, thresholds, fairness, CI | 25 |
| E6 Guardrails | PII/secrets/injection, content safety, policy, audit | 20 |
| E7 Observability | Trace schema, Monitor, dashboards, alerts | 15 |
| E8 Feedback loop | Capture, certification queue, routing to golden | 15 |
| E9 Governance & audit | Approval workflow, audit explorer, RBAC | 15 |
| E10 Ops Platform (shell + 11 modules) | Frontend shell, nav, all module UIs | 45 |
| E11 Data ingestion | Scheduled ingest, validation, backfill | 15 |
| E12 AI pipeline rebuild | denoise/analysis/summary on seam; parity | 25 |
| E13 KPI/scoring engine | Codify rulebooks, composite score, fairness | 25 |
| E14 Coaching dashboard | Scorecards, behaviour, comparisons, tips | 25 |
| E15 Chatbot | NL->SQL, scope injection, UI, history/feedback | 20 |
| E16 Reporting & notifications | Scheduled reports, export, email/Teams | 12 |
| E17 User mgmt & admin | Entra SSO, RBAC, provisioning, admin panel | 15 |
| E18 Testing & UAT | Test suites, eval-gate in CI, UAT | 20 |
| E19 Rollout & enablement | Pilot, remediate, full rollout, training, hypercare | 25 |
| E20 Reusability packaging | Generic vs APIX-specific; onboarding playbook | 8 |
| Total (Phase 1 indicative) |  | ~430 days |

Estimates are planning-level, pre-team-confirmation. With the full team (~8-10 FTE) ~5-7 months elapsed; with the focused core (~4 FTE) ~9-11 months (confirmed by D-6).

# 5. Milestones

M1 decisions closed | M2 core + Ops shell | M3 APIX pipeline parity | M4 dashboard+chatbot | M5 UAT pass | M6 pilot | M7 full rollout.

# 6. Team Structure

| Role | FTE (full) | FTE (core) | Primary area |
| --- | --- | --- | --- |
| Eng Lead / Architect | 1 | 1 | Architecture, governance, client |
| Cloud/DevOps | 1 | 0.5 | Env, CI/CD, infra, observability |
| Platform Eng | 1.5 | 1 | Config core, Ops backend, auth |
| AI/LLM Eng | 2 | 1 | LLMOps core, pipeline, chatbot |
| Data Eng | 1 | 1 | Ingestion, KPI engine, reporting |
| Frontend Eng | 1.5 | 1 | Ops Platform UI, dashboard |
| QA/Eval Eng | 1 | 0.5 | Golden data, eval, testing |
| Security/Compliance | 0.75 | shared | PII, audit, compliance mapping |
| BA/SME Liaison | 0.75 | shared | Decisions, KPI validation |
| UX Designer | 0.5 | shared | Ops + dashboard design |

# 7. Testing, Deployment & Governance

Testing: unit + integration per module; pipeline parity vs POC; evaluation gate on every LLM change; security/guardrail tests; UAT; fairness validation.

Deployment: pilot one program -> remediate -> full rollout -> training -> hypercare.

Governance: weekly status; decision-register review; change control via eval+approval; phase-gate reviews.

# 8. Open Items

Consolidated in RAID 3.1 (D-1..D-6, O-1..O-4). Estimates and timeline firm up once D-2/D-3/D-6 confirm.